---

## ✅ FINAL INTEGRATION CHECKLIST

After completing all steps:

- [ ] **Step 1:** `core-workflow.md` copied to `99-reference/execution-guides/common/`

- [ ] **Step 2:** `core-workflow-hybrid.md` created with gate integration

- [ ] **Step 3:** Execution guides index updated with core-workflow reference

- [ ] **Step 4:** Root README.md updated with usage instructions

- [ ] **Step 5:** AI initialization script created

- [ ] **Step 6:** AI prompt template created

- [ ] **Step 7:** Integration tests passed

- [ ] **Step 8:** Training guide updated

- [ ] **Verify:** AI can access and follow core-workflow

- [ ] **Verify:** Gate checkpoints documented

- [ ] **Verify:** Team understands hybrid model

---

## 🎯 Quick Command Summary

```bash

# Copy core-workflow

cp /path/to/system1/core-workflow.md 99-reference/execution-guides/common/

# Test integration

./scripts/test-integration.sh

# Initialize AI session

./scripts/init-ai-session.sh

# Check status

./scripts/check-aidlc-status.sh

# Start AI with hybrid workflow

cat AI-PROMPT-TEMPLATE.md

# Then paste customized prompt to AI

🎯 IMPLEMENTATION GUIDE: Hybrid Enterprise-Ready AI-DLC System

📋 Table of Contents

- Implementation Overview

- Phase 1: Foundation Setup

- Phase 2: Governance Integration

- Phase 3: Execution Procedures

- Phase 4: Enforcement Mechanisms

- Phase 5: Validation & Rollout

- Quick Start Guide

- Migration Paths

🎯 IMPLEMENTATION OVERVIEW

What You're Building

A unified AI-DLC system that combines:

- System 2's governance structure (phase gates, roles, security)

- System 1's execution detail (stage procedures, AI guidance, checkboxes)

Implementation Timeline

- Small Team (2-5 people): 2-3 weeks

- Medium Team (6-20 people): 4-6 weeks

- Enterprise (20+ people): 8-12 weeks

Prerequisites

- Git repository access

- Basic understanding of both systems

- Stakeholder buy-in

- Tool access (GitHub/GitLab/Bitbucket)

📦 PHASE 1: FOUNDATION SETUP (Week 1)

Step 1.1: Create Hybrid Repository Structure

Create a new repository with the following structure:

bash

Copy code

# Create root directory mkdir aidlc-hybrid && cd aidlc-hybrid # Create governance structure (from System 2) mkdir -p 00-governance mkdir -p 01-inception/{plans,reverse-engineering,requirements,user-stories,application-design} mkdir -p 02-construction/{plans,units,build-test} mkdir -p 03-operations mkdir -p 99-reference/{execution-guides,role-guides,standards,templates} # Create execution guide directories (from System 1) mkdir -p 99-reference/execution-guides/{common,inception,construction,operations}

Step 1.2: Initialize Core Governance Files

File: 00-governance/aidlc-state.md

markdown

Copy code

# AI-DLC State Tracking ## Project Information - **Project Name:** [Your Project Name] - **Project Type:** [Greenfield/Brownfield] - **Start Date:** [ISO timestamp] - **Current Phase:** Phase 0 - Repository Initialization - **Current Stage:** Governance Setup - **Adaptive Depth Level:** [To be determined at Gate 1] ## Workspace State - **Existing Code:** [Yes/No] - **Workspace Root:** [Absolute path] - **Programming Languages:** [List if brownfield] - **Build System:** [Maven/Gradle/npm/etc. if found] ## Code Location Rules - **Application Code:** Workspace root (NEVER in aidlc-docs/) - **Documentation:** aidlc-docs/ only - **Structure Pattern:** [To be determined based on project type] ## Current Gate Status - **Active Gate:** Gate 0 - Repository & Governance Initialization - **Gate Status:** IN PROGRESS - **Blocking Conditions:** None - **Next Gate:** Gate 1 - Inception Entry ## Phase Progress ### 🔵 INCEPTION PHASE - [ ] Workspace Detection - [ ] Reverse Engineering (if brownfield) - [ ] Requirements Analysis - [ ] User Stories (conditional) - [ ] Workflow Planning - [ ] Application Design (conditional) - [ ] Units Generation (conditional) ### 🟢 CONSTRUCTION PHASE - [ ] Per-Unit Design & Code Generation - [ ] Build and Test ### 🟡 OPERATIONS PHASE - [ ] Operations (future) ## Execution Plan Summary - **Total Stages:** [To be determined] - **Stages to Execute:** [To be determined] - **Stages to Skip:** [To be determined] ## Last Updated - **Timestamp:** [ISO timestamp] - **Updated By:** [Name/Role] - **Reason:** Initial creation

File: 00-governance/audit.md

markdown

Copy code

# AI-DLC Audit Log ## Purpose Immutable chronological record of all decisions, approvals, and material interactions. ## Logging Rules - ISO 8601 timestamps (mandatory) - Append-only (no edits, no deletions) - Human + AI actions logged equally - Complete raw user input (never summarized) --- ## Audit Entries ### Repository Initialization **Timestamp:** [ISO timestamp] **Event Type:** Project Start **Actor:** [Name/Role] **Action:** Repository structure created **Context:** AI-DLC hybrid system initialization **Artifacts Created:** - 00-governance/aidlc-state.md - 00-governance/audit.md - 00-governance/phase-gates.md - 00-governance/ownership.md ---

File: 00-governance/phase-gates.md

markdown

Copy code

# AI-DLC Phase Gates ## Purpose Define mandatory phase gates with explicit approval criteria and authorities. ## Gate Enforcement Rules - Gates are sequential and mandatory - Gate approvals must be documented in audit.md - Retroactive approvals are prohibited - Emergency bypass requires executive approval + audit logging --- ## Gate 0 — Repository & Governance Initialization **Objective:** Establish controlled execution environment before analysis begins. **Entry Criteria:** - Repository created - Governance structure established **Mandatory Artifacts:** - ✅ README.md (project overview) - ✅ aidlc-state.md (initialized) - ✅ audit.md (initialized) - ✅ phase-gates.md (this file) - ✅ ownership.md (role assignments) **Validation Checklist:** - [ ] Single shared repository confirmed - [ ] Ownership model defined - [ ] Audit logging enabled - [ ] Execution guides accessible **Approval Authority:** Program/Delivery Lead **Exit Criteria:** Execution environment is governance-ready. --- ## Gate 1 — Inception Entry Approval **Objective:** Confirm clarity of intent and readiness for structured analysis. **Entry Criteria:** - Gate 0 approved - Initial user request captured **Mandatory Artifacts:** - ✅ Workspace detection completed - ✅ Greenfield/Brownfield determination - ✅ Adaptive depth level declared - ✅ Initial request logged in audit.md **Validation Checklist:** - [ ] System context understood - [ ] Existing assets identified (if brownfield) - [ ] Depth level appropriate for risk/complexity - [ ] No blind start **Approval Authority:** Architect **Exit Criteria:** System context understood, analysis may begin. --- ## Gate 2 — Requirements Validation **Objective:** Lock business intent and prevent assumption-driven execution. **Entry Criteria:** - Gate 1 approved - Requirements analysis complete **Mandatory Artifacts:** - ✅ requirements.md (validated) - ✅ requirement-verification-questions.md (answered) - ✅ Scope and exclusions confirmed - ✅ Change classification (bug/enhancement/migration) **Validation Checklist:** - [ ] Intent is unambiguous - [ ] All clarifying questions answered - [ ] No conflicting requirements - [ ] Scope boundaries defined - [ ] Risk acknowledged **Approval Authority:** Business Analyst, Product Owner **Exit Criteria:** Requirements approved; design may begin. **Golden Rule:** No validated requirements → No design. --- ## Gate 3 — Design Readiness **Objective:** Approve high-level system structure before decomposition. **Entry Criteria:** - Gate 2 approved - Application design complete (if applicable) - Workflow planning complete **Mandatory Artifacts:** - ✅ execution-plan.md (workflow plan) - ✅ application-design.md (if applicable) - ✅ unit-of-work.md (if units required) - ✅ component-dependency.md (if applicable) **Validation Checklist:** - [ ] Architecture is coherent - [ ] Component boundaries clear - [ ] Dependencies identified - [ ] Units are independently executable (if applicable) - [ ] Risk assessment complete **Approval Authority:** Solution Architect **Exit Criteria:** Design is fit for controlled construction. --- ## Gate 4 — Construction Entry (Per Unit) **Objective:** Authorize build for a specific Unit of Work. **Entry Criteria:** - Gate 3 approved - Unit design complete **Mandatory Artifacts (Per Unit):** - ✅ functional-design.md (if applicable) - ✅ nfr-requirements.md (if applicable) - ✅ nfr-design.md (if applicable) - ✅ infrastructure-design.md (if applicable) **Validation Checklist:** - [ ] Business logic explicitly designed - [ ] Quality attributes (NFR) explicitly designed - [ ] Infrastructure mapped - [ ] Risks addressed **Approval Authority:** Technical Lead, Architect **Exit Criteria:** Unit approved for code generation. --- ## Gate 5 — Code Generation Approval **Objective:** Explicitly authorize AI-driven code generation. **Entry Criteria:** - Gate 4 approved (for current unit) - Code generation plan created **Mandatory Artifacts:** - ✅ {unit-name}-code-generation-plan.md (approved) - ✅ Code generation checklist complete - ✅ Test strategy documented - ✅ Human reviewers assigned **Validation Checklist:** - [ ] Plan follows approved design - [ ] No improvisation allowed - [ ] Tests planned alongside code - [ ] AI scope constrained to plan - [ ] File paths documented (never aidlc-docs/) **Approval Authority:** Architect, Senior Developer **Exit Criteria:** AI may generate code per approved plan. **Golden Rule:** No plan approval → No code. --- ## Gate 6 — Build & Test Validation **Objective:** Confirm production-grade readiness of the unit/system. **Entry Criteria:** - Gate 5 approved - Code generation complete - Tests executed **Mandatory Artifacts:** - ✅ Unit test results (passed) - ✅ Integration test results (passed) - ✅ build-and-test-summary.md - ✅ NFR evidence (performance/security as applicable) **Validation Checklist:** - [ ] Functional correctness verified - [ ] NFR benchmarks met (if applicable) - [ ] No critical defects open - [ ] Code review completed - [ ] Security scan passed (if applicable) **Approval Authority:** QA Lead, Engineering Manager **Exit Criteria:** Unit/system is production-ready. --- ## Gate 7 — Phase Completion Approval **Objective:** Authorize transition to Operations or next delivery increment. **Entry Criteria:** - Gate 6 approved - All units complete **Mandatory Artifacts:** - ✅ build-and-test-summary.md (final) - ✅ audit.md (updated) - ✅ aidlc-state.md (phase complete) - ✅ Traceability complete **Validation Checklist:** - [ ] All planned work complete - [ ] All tests passed - [ ] All decisions documented - [ ] No undocumented exceptions - [ ] Ready for deployment **Approval Authority:** Program Sponsor, CXO Delegate **Exit Criteria:** Phase formally closed; Operations may begin. --- ## Emergency Exception Handling **When gates may be bypassed:** - Production incident requiring immediate fix - Executive mandate with documented justification **Required Actions:** - Document exception in audit.md - Explain reason and risk - Define compensating controls - Obtain executive approval - Set remediation timeline - Review at next gate

File: 00-governance/ownership.md

markdown

Copy code

# AI-DLC Ownership Model ## Purpose Define clear, non-overlapping role boundaries and artifact ownership. ## Core Principle Every artifact has a single accountable owner. No role can approve its own downstream work. --- ## Role Definitions ### 1. Business Analyst (BA) / Product Owner **Primary Accountability:** - Business intent clarity - Requirements correctness - Acceptance criteria definition **Owns Artifacts:** - `requirements.md` - `requirement-verification-questions.md` - `user-stories.md` - `personas.md` **Decision Authority:** - What problem is being solved - What success means - What is in/out of scope **Gate Involvement:** - Gate 2 — Requirements Validation (primary approver) **Explicitly NOT Responsible For:** - Architecture decisions - Technology selection - Code-level design --- ### 2. Architect / Solution Architect **Primary Accountability:** - Structural integrity of system - Component boundaries - NFR alignment - Technology decisions **Owns Artifacts:** - `architecture.md` (brownfield reverse engineering) - `application-design.md` - `component-dependency.md` - `nfr-design-patterns.md` - `infrastructure-design.md` **Decision Authority:** - How the system is structured - Service boundaries - Design patterns and trade-offs - Technology stack selection **Gate Involvement:** - Gate 1 — Inception Entry (primary approver) - Gate 3 — Design Readiness (primary approver) - Gate 4 — Construction Entry (co-approver) - Gate 5 — Code Generation Approval (co-approver) **Explicitly NOT Responsible For:** - Business prioritization - Detailed implementation logic - Test execution --- ### 3. Developer / Engineer **Primary Accountability:** - Correctness of implementation - Code quality - Unit-level test coverage **Owns Artifacts:** - `{unit-name}-code-generation-plan.md` - Source code - Unit tests - Build scripts **Decision Authority:** - Implementation approach within approved design - Refactoring inside unit boundaries - Technical implementation details **Gate Involvement:** - Gate 5 — Code Generation Approval (support) - Gate 6 — Build & Test Validation (support) **Explicitly NOT Responsible For:** - Changing requirements - Altering architecture - Approving their own work --- ### 4. QA / Testing Role **Primary Accountability:** - Validation of behavior and quality - Risk exposure identification - Test completeness **Owns Artifacts:** - `test-strategy.md` - `integration-test-instructions.md` - `e2e-test-instructions.md` - Test results - Defect logs **Decision Authority:** - Whether system meets acceptance criteria - Whether risks are acceptable - When quality is sufficient **Gate Involvement:** - Gate 6 — Build & Test Validation (primary approver) **Explicitly NOT Responsible For:** - Fixing defects - Modifying requirements - Approving incomplete coverage --- ### 5. Platform / Infrastructure / DevOps **Primary Accountability:** - Runtime stability - Deployment safety - Environment consistency **Owns Artifacts:** - `infrastructure-design.md` (co-owned with Architect) - `deployment-architecture.md` - `shared-infrastructure.md` - CI/CD configurations **Decision Authority:** - Cloud services used - Deployment strategy - Rollback strategy - Environment configurations **Gate Involvement:** - Gate 4 — Construction Entry (support for infrastructure) - Gate 7 — Phase Completion (support for operations readiness) **Explicitly NOT Responsible For:** - Business logic - Application behavior - Test design --- ### 6. Program / Delivery Lead **Primary Accountability:** - Overall delivery coordination - Risk management - Governance enforcement **Owns Artifacts:** - `aidlc-state.md` - `phase-gates.md` - `ownership.md` (this file) - `risk-register.md` **Decision Authority:** - Adaptive depth level selection - Exception approvals (low-risk) - Timeline and resource allocation **Gate Involvement:** - Gate 0 — Repository Initialization (primary approver) - Gate 7 — Phase Completion (co-approver) **Explicitly NOT Responsible For:** - Technical design decisions - Requirements definition - Code approval --- ## AI's Role (Explicitly Defined) **AI is treated as:** - A role-aware accelerator - A non-authoritative participant - A proposal generator **AI May:** - Generate artifact drafts - Propose designs and implementations - Surface risks and questions - Execute approved plans **AI May NOT:** - Approve phase gates - Override role ownership - Make final decisions - Bypass governance controls - Self-approve its own outputs --- ## Artifact-to-Owner Mapping | Artifact | Primary Owner | Co-Owners | Gate Dependency | |----------|---------------|-----------|-----------------| | `aidlc-state.md` | Delivery Lead | All | All gates | | `audit.md` | Platform | All (log entries) | All gates | | `requirements.md` | BA | - | Gate 2 | | `architecture.md` | Architect | - | Gate 1 (brownfield) | | `user-stories.md` | BA | - | Gate 2 (conditional) | | `application-design.md` | Architect | - | Gate 3 | | `unit-of-work.md` | Architect | Developer | Gate 3 | | `functional-design.md` | Architect | Developer | Gate 4 | | `nfr-requirements.md` | Architect | - | Gate 4 | | `nfr-design.md` | Architect | - | Gate 4 | | `infrastructure-design.md` | Architect | Platform | Gate 4 | | `{unit}-code-generation-plan.md` | Developer | Architect | Gate 5 | | Source Code | Developer | - | Gate 5 | | Unit Tests | Developer | QA | Gate 5 | | `test-strategy.md` | QA | - | Gate 6 | | Test Results | QA | Developer | Gate 6 | --- ## Cross-Role Collaboration Rules ### 1. Approval Rules - **No self-approval:** Cannot approve your own artifacts - **Downstream approval:** Upstream roles approve downstream work - **Example:** Architect approves Developer's code generation plan ### 2. Review Rules - **Peer review:** Encouraged within same role - **Cross-role review:** Mandatory at phase gates - **AI review:** AI cannot substitute for human review ### 3. Escalation Rules - **Role conflict:** Escalate to Delivery Lead - **Technical conflict:** Escalate to Architect - **Business conflict:** Escalate to Product Owner - **Urgent issues:** Escalate to Program Sponsor ### 4. Communication Rules - **Artifact-first:** Use artifacts to communicate (not just chat) - **Asynchronous:** Favor async updates in audit.md - **Gate convergence:** Synchronous discussions at gates --- ## RACI Matrix Summary | Activity | BA | Architect | Developer | QA | Platform | Lead | |----------|----|-----------|-----------|----|----------|------| | Requirements | **A** | C | I | I | I | R | | Architecture | C | **A** | I | I | C | R | | Design | I | **A** | C | I | C | R | | Code Generation | I | C | **A** | I | I | R | | Testing | C | I | C | **A** | I | R | | Deployment | I | C | C | I | **A** | R | | Gate Approval | Varies by gate | Varies | Varies | Varies | Varies | **R** | **Legend:** - **R**esponsible: Does the work - **A**ccountable: Final decision authority - **C**onsulted: Input required - **I**nformed: Kept updated --- ## Contact Information | Role | Name | Contact | Backup | |------|------|---------|--------| | BA/Product Owner | [Name] | [Email] | [Name] | | Architect | [Name] | [Email] | [Name] | | Lead Developer | [Name] | [Email] | [Name] | | QA Lead | [Name] | [Email] | [Name] | | Platform Lead | [Name] | [Email] | [Name] | | Delivery Lead | [Name] | [Email] | [Name] | --- ## Last Updated - **Date:** [ISO timestamp] - **By:** [Name/Role] - **Reason:** [Initial creation/Update reason]

Step 1.3: Create README.md

File: README.md

markdown

Copy code

# AI-DLC Hybrid System ## Overview This repository implements a hybrid AI-Driven Development Life Cycle (AI-DLC) system that combines: - **Robust governance framework** with formal phase gates and role-based controls - **Detailed execution guidance** with step-by-step AI procedures ## Current Status - **Phase:** Phase 0 - Repository Initialization - **Active Gate:** Gate 0 - **Status:** IN PROGRESS ## Quick Navigation - [Governance Files](./00-governance/) - Core control files - [Inception Artifacts](./01-inception/) - Requirements and design - [Construction Artifacts](./02-construction/) - Code and tests - [Execution Guides](./99-reference/execution-guides/) - Detailed procedures - [Role Guides](./99-reference/role-guides/) - Role-specific instructions ## Repository Structure

aidlc-hybrid/ ├── 00-governance/ # Phase gates, ownership, state, audit ├── 01-inception/ # Requirements, design, planning ├── 02-construction/ # Code generation, testing ├── 03-operations/ # Deployment (future) └── 99-reference/ # Guides, standards, templates

markdown

Copy code

## Key Files - **[aidlc-state.md](./00-governance/aidlc-state.md)** - Current lifecycle state - **[audit.md](./00-governance/audit.md)** - Decision audit trail - **[phase-gates.md](./00-governance/phase-gates.md)** - Gate criteria - **[ownership.md](./00-governance/ownership.md)** - Role assignments ## How to Start 1. Review [phase-gates.md](./00-governance/phase-gates.md) 2. Assign roles in [ownership.md](./00-governance/ownership.md) 3. Complete Gate 0 validation checklist 4. Begin Inception Phase ## Roles and Responsibilities - **Business Analyst:** Requirements and acceptance criteria - **Architect:** System structure and technical decisions - **Developer:** Implementation and code quality - **QA:** Quality validation and testing - **Platform:** Infrastructure and deployment - **Delivery Lead:** Overall coordination and governance ## Contact - **Delivery Lead:** [Name] ([Email]) - **Architect:** [Name] ([Email]) ## License [Your License]

📚 PHASE 2: GOVERNANCE INTEGRATION (Week 2)

Step 2.1: Integrate Execution Guides from System 1

Copy all execution rule files from System 1 into the reference directory:

bash

Copy code

# Copy System 1 files to execution guides cp system1/common/*.md 99-reference/execution-guides/common/ cp system1/inception/*.md 99-reference/execution-guides/inception/ cp system1/construction/*.md 99-reference/execution-guides/construction/

Step 2.2: Create Master Execution Guide Index

File: 99-reference/execution-guides/README.md

markdown

Copy code

# AI-DLC Execution Guides ## Purpose Detailed step-by-step procedural guidance for AI assistants executing AI-DLC workflows. ## Guide Organization ### Common Guides (Apply to All Phases) - [Core Workflow](./common/core-workflow.md) - Main workflow orchestration - [Error Handling](./common/error-handling.md) - Error recovery procedures - [Content Validation](./common/content-validation.md) - Content quality rules - [Depth Levels](./common/depth-levels.md) - Adaptive detail guidelines - [Overconfidence Prevention](./common/overconfidence-prevention.md) - Question generation - [Session Continuity](./common/session-continuity.md) - Session resumption - [Terminology](./common/terminology.md) - Standard vocabulary - [Process Overview](./common/process-overview.md) - High-level workflow - [Question Format Guide](./common/question-format-guide.md) - Question standards - [ASCII Diagram Standards](./common/ascii-diagram-standards.md) - Diagram requirements ### Inception Phase Guides - [Workspace Detection](./inception/workspace-detection.md) - [Reverse Engineering](./inception/reverse-engineering.md) - [Requirements Analysis](./inception/requirements-analysis.md) - [User Stories](./inception/user-stories.md) - [Application Design](./inception/application-design.md) - [Units Generation](./inception/units-generation.md) - [Workflow Planning](./inception/workflow-planning.md) ### Construction Phase Guides - [Functional Design](./construction/functional-design.md) - [NFR Requirements](./construction/nfr-requirements.md) - [NFR Design](./construction/nfr-design.md) - [Infrastructure Design](./construction/infrastructure-design.md) - [Code Generation](./construction/code-generation.md) - [Build and Test](./construction/build-and-test.md) ## How AI Should Use These Guides ### Before Starting Any Stage 1. Read relevant execution guide for the stage 2. Load common guides (core-workflow, error-handling, content-validation) 3. Check current gate status in `00-governance/aidlc-state.md` 4. Verify gate approval exists before proceeding ### During Stage Execution 1. Follow step-by-step procedures in execution guide 2. Apply overconfidence prevention (ask questions when uncertain) 3. Update plan checkboxes immediately after each step 4. Log all decisions and user inputs in `00-governance/audit.md` ### After Stage Completion 1. Update `00-governance/aidlc-state.md` 2. Present completion message per guide format 3. Wait for explicit user approval 4. Check if gate validation is required ### Gate Integration Execution guides provide tactical "how" while phase gates provide strategic "when": - **Execution Guide:** How to execute the stage (detailed steps) - **Phase Gate:** When to proceed to next phase (approval criteria) ## Key Principles 1. **No hardcoded logic** - Follow guides exactly 2. **Update checkboxes immediately** - Track progress in real-time 3. **Ask questions** - Default to questioning when uncertain 4. **Validate content** - Check Mermaid, ASCII, markdown before writing 5. **Never proceed with ambiguity** - Create follow-up questions 6. **Respect gate boundaries** - Stop at gates, wait for approval ## Last Updated [ISO timestamp] - [Name/Role]

Step 2.3: Integrate System 2 Policy Documents

Copy System 2 governance documents:

bash

Copy code

# Copy System 2 governance files cp system2/01-aidlc-overview.md 99-reference/ cp system2/02-phases-and-stages.md 99-reference/ cp system2/03-phase-gates-reference.md 99-reference/ cp system2/04-artifact-catalog.md 99-reference/ cp system2/05-adaptive-depth-model.md 99-reference/ cp system2/06-questioning-and-overconfidence.md 99-reference/ cp system2/07-content-validation-rules.md 99-reference/ cp system2/08-audit-and-state-management.md 99-reference/ cp system2/09-role-boundaries.md 99-reference/ cp system2/10-collaboration-model.md 99-reference/ cp system2/11-git-and-repo-governance.md 99-reference/ cp system2/12-ai-code-generation-rules.md 99-reference/ cp system2/13-testing-and-quality-standards.md 99-reference/ cp system2/14-risk-and-exception-handling.md 99-reference/ cp system2/15-future-operations-roadmap.md 99-reference/ cp system2/16-security-ip.md 99-reference/

Step 2.4: Create Role Guides

Copy role guides from System 2:

bash

Copy code

cp system2/ba-guide.md 99-reference/role-guides/ cp system2/architect-guide.md 99-reference/role-guides/ cp system2/developer-guide.md 99-reference/role-guides/ cp system2/qa_guide.md 99-reference/role-guides/

🔧 PHASE 3: EXECUTION PROCEDURES (Week 3)

Step 3.1: Create Hybrid Execution Master Guide

File: 99-reference/execution-guides/HYBRID-EXECUTION-GUIDE.md

markdown

Copy code

# Hybrid AI-DLC Execution Guide ## Purpose This guide bridges System 1's detailed execution procedures with System 2's governance gates. ## Core Integration Principle **Execution guides tell AI "HOW" to do work. Phase gates tell humans "WHEN" to approve.** --- ## Execution Flow with Gates ### Phase 0: Repository Initialization **Gate 0: Repository & Governance Initialization** - **Approval Authority:** Delivery Lead - **Status Check:** `00-governance/aidlc-state.md` → Current Gate = Gate 0 **Execution:** 1. Repository structure created ✅ (completed in Phase 1 of implementation) 2. Core governance files initialized ✅ 3. Role assignments documented ✅ 4. Execution guides accessible ✅ **Gate 0 Exit:** - [ ] Validation checklist complete - [ ] Delivery Lead approval logged in audit.md - [ ] Update `aidlc-state.md`: Current Gate = Gate 1 --- ### Phase 1: Inception #### **Gate 1: Inception Entry Approval** - **Approval Authority:** Architect - **Status Check:** `aidlc-state.md` → Current Gate = Gate 1 **Before Starting Inception Stages:** 1. Check Gate 1 entry criteria in `00-governance/phase-gates.md` 2. Confirm Gate 0 was approved 3. Verify workspace context available #### **Stage 1.1: Workspace Detection** **Execution Guide:** `99-reference/execution-guides/inception/workspace-detection.md` **Procedure:** 1. Load workspace-detection.md execution guide 2. Execute all steps per guide: - Check for existing aidlc-state.md (resume detection) - Scan workspace for existing code - Determine greenfield vs brownfield - Record workspace root path - Create/update aidlc-state.md 3. Log findings in `00-governance/audit.md`: ```markdown ### Workspace Detection Complete **Timestamp:** [ISO timestamp] **Actor:** AI Assistant **Findings:** - Project Type: [Greenfield/Brownfield] - Workspace Root: [Path] - Existing Code: [Yes/No] - Programming Languages: [List] **Next Stage:** [Reverse Engineering / Requirements Analysis]

- Update 00-governance/aidlc-state.md:

  - Mark "Workspace Detection" as [x] complete

  - Update "Current Stage"

- Automatically proceed to next stage (no user approval needed per guide)

Stage 1.2: Reverse Engineering (Conditional - Brownfield Only)

Execution Guide: 99-reference/execution-guides/inception/reverse-engineering.md

Gate Integration:

- Required for Gate 1 exit (if brownfield)

Procedure:

- Check condition: Execute only if brownfield AND no existing artifacts

- Load reverse-engineering.md execution guide

- Execute all steps per guide:

  - Multi-package discovery

  - Generate business-overview.md

  - Generate architecture.md

  - Generate code-structure.md

  - Generate api-documentation.md

  - Generate component-inventory.md

  - Generate technology-stack.md

  - Generate dependencies.md

  - Generate code-quality-assessment.md

  - Create timestamp file

- Store artifacts in: 01-inception/reverse-engineering/

- Log completion in 00-governance/audit.md

- Update 00-governance/aidlc-state.md

- Present completion message per guide

- Wait for explicit user approval (guide requirement)

- Log user approval in 00-governance/audit.md:

markdown

Copy code

### Reverse Engineering User Approval **Timestamp:** [ISO timestamp] **User Response:** "[Complete raw user input]" **Action:** Approved to proceed

Gate 1 Preparation: After reverse engineering (if applicable), prepare for Gate 1 exit:

- Artifacts ready: workspace-detection.md, architecture.md (if brownfield)

- Log in audit.md: "Ready for Gate 1 approval"

Gate 1 Exit Validation

Checklist:

- Workspace scan complete

- Greenfield/Brownfield determined

- Reverse engineering complete (if brownfield)

- Artifacts stored in 01-inception/reverse-engineering/

- System context understood

Approval Process:

- AI creates summary in audit.md:

markdown

Copy code

### Gate 1 Exit - Approval Request **Timestamp:** [ISO timestamp] **Requested By:** AI Assistant **Current Phase:** Inception Entry **Completed Artifacts:** - workspace-detection.md - architecture.md (if brownfield) - component-inventory.md (if brownfield) **Validation Checklist:** [Summary] **Recommendation:** Ready for Gate 1 approval **Required Approver:** Architect

- Architect reviews and approves (in audit.md):

markdown

Copy code

### Gate 1 Approval **Timestamp:** [ISO timestamp] **Approver:** [Architect Name] **Role:** Solution Architect **Decision:** APPROVED **Comments:** [Any comments] **Next Gate:** Gate 2 - Requirements Validation

- AI updates 00-governance/aidlc-state.md:

  - Current Gate: Gate 2

  - Gate 1: APPROVED - [timestamp]

  - Current Stage: Requirements Analysis

Stage 1.3: Requirements Analysis

Execution Guide: 99-reference/execution-guides/inception/requirements-analysis.md

Gate Integration:

- Required for Gate 2 exit

Procedure:

- Check Gate 1 is approved (aidlc-state.md)

- Load requirements-analysis.md execution guide

- Load reverse engineering context (if brownfield)

- Execute all steps per guide:

  - Analyze user request (intent analysis)

  - Determine requirements depth (Minimal/Standard/Comprehensive)

  - Assess current requirements

  - Thorough completeness analysis

  - Generate clarifying questions (proactive approach)

  - Create requirement-verification-questions.md

  - Wait for user answers

  - Analyze answers for ambiguities

  - Create follow-up questions if needed

  - Generate requirements.md

- Store artifacts in: 01-inception/requirements/

- Log all user inputs in 00-governance/audit.md (complete raw input)

- Update 00-governance/aidlc-state.md

- Present completion message per guide

- Wait for explicit user approval

- Log user approval in audit.md

Gate 2 Preparation:

- Artifacts ready: requirements.md, requirement-verification-questions.md

- All questions answered and ambiguities resolved

- Log: "Ready for Gate 2 approval"

Gate 2 Exit Validation

Checklist:

- requirements.md complete and validated

- requirement-verification-questions.md answered

- All ambiguities resolved

- Scope and exclusions defined

- Change classification documented

- Risk acknowledged

Approval Process:

- AI creates approval request in audit.md (similar format as Gate 1)

- Business Analyst and Product Owner review and approve

- AI updates aidlc-state.md: Current Gate = Gate 3

Golden Rule Enforcement: If requirements are not clear, Gate 2 cannot be approved. Execution pauses.

Stage 1.4: User Stories (Conditional)

Execution Guide: 99-reference/execution-guides/inception/user-stories.md

Conditional Execution: Follow intelligent assessment from guide to determine if needed.

Two-Part Structure:

- Part 1 - Planning: Create story generation plan with questions

- Part 2 - Generation: Execute approved plan

Procedure:

- Perform intelligent assessment per guide

- If needed, execute Part 1:

  - Create story-generation-plan.md

  - Generate questions

  - Wait for answers

  - Analyze for ambiguities

  - Get plan approval

- Execute Part 2:

  - Load approved plan

  - Generate stories.md

  - Generate personas.md

- Store artifacts in: 01-inception/user-stories/

- Log in audit.md

- Update aidlc-state.md

- Present completion message

- Wait for user approval

Stage 1.5: Workflow Planning

Execution Guide: 99-reference/execution-guides/inception/workflow-planning.md

Gate Integration:

- Required for Gate 3 exit

Procedure:

- Load all prior context per guide

- Execute detailed scope and impact analysis

- Determine which phases to execute (adaptive)

- Declare adaptive depth level:

  - Minimal / Standard / Comprehensive

  - Document in execution-plan.md

  - Record in aidlc-state.md

- Multi-module coordination (if brownfield)

- Generate workflow visualization (validate Mermaid!)

- Create execution-plan.md

- Store in: 01-inception/plans/

- Update aidlc-state.md: Adaptive Depth Level = [level]

- Log in audit.md

- Present recommendations (emphasize user control)

- Wait for user approval

Depth Level Integration: System 1's depth determination + System 2's formal declaration:

- AI assesses appropriate depth (System 1 logic)

- Depth level declared in execution-plan.md

- Recorded in aidlc-state.md (System 2 tracking)

- Will be validated at Gate 3

Stage 1.6: Application Design (Conditional)

Execution Guide: 99-reference/execution-guides/inception/application-design.md

Procedure: (Follow similar pattern as previous stages)

Stage 1.7: Units Generation (Conditional)

Execution Guide: 99-reference/execution-guides/inception/units-generation.md

Procedure: (Follow similar pattern as previous stages)

Gate 3 Exit Validation: Design Readiness

Checklist:

- execution-plan.md complete (workflow plan)

- Adaptive depth level declared and appropriate

- application-design.md complete (if applicable)

- unit-of-work.md complete (if units required)

- Architecture coherent

- Dependencies identified

- Risk assessment complete

Approval Process:

- AI creates approval request in audit.md

- Solution Architect reviews and approves

- Architect validates:

  - Depth level is appropriate for risk/complexity

  - Architecture decisions are sound

  - Dependencies are manageable

- AI updates aidlc-state.md: Current Gate = Gate 4, Current Phase = Construction

Phase 2: Construction

Per-Unit Loop Structure

For each unit of work, execute:

- Gate 4 entry validation (per unit)

- Functional Design (conditional)

- NFR Requirements (conditional)

- NFR Design (conditional)

- Infrastructure Design (conditional)

- Gate 5 entry validation

- Code Generation (always) - Part 1 Planning

- Gate 5 approval

- Code Generation (always) - Part 2 Generation

- Move to next unit OR proceed to Build & Test

Gate 4: Construction Entry (Per Unit)

Before Starting Unit Design:

- Check Gate 3 is approved

- Load unit definition from unit-of-work.md

- Verify unit is next in sequence

Gate 4 Checklist (Per Unit):

- Gate 3 approved (first unit) OR previous unit complete

- Unit clearly defined

- Unit dependencies identified

Approval Authority: Technical Lead, Architect

Stage 2.1: Functional Design (Per Unit, Conditional)

Execution Guide: 99-reference/execution-guides/construction/functional-design.md

Procedure:

- Check execution condition per guide

- Load unit context

- Create functional-design-plan.md

- Generate questions (context-appropriate)

- Collect and analyze answers

- Generate artifacts:

  - business-logic-model.md

  - business-rules.md

  - domain-entities.md

- Store in: 02-construction/{unit-name}/functional-design/

- Log in audit.md

- Update plan checkboxes

- Update aidlc-state.md

- Present standardized 2-option completion message (System 1 requirement)

- Wait for explicit approval

- Log approval in audit.md

Critical: MUST use standardized 2-option completion message (no emergent 3-option behavior)

Stage 2.2: NFR Requirements (Per Unit, Conditional)

Execution Guide: 99-reference/execution-guides/construction/nfr-requirements.md

(Similar procedure as Functional Design)

Stage 2.3: NFR Design (Per Unit, Conditional)

Execution Guide: 99-reference/execution-guides/construction/nfr-design.md

(Similar procedure)

Stage 2.4: Infrastructure Design (Per Unit, Conditional)

Execution Guide: 99-reference/execution-guides/construction/infrastructure-design.md

(Similar procedure)

Gate 4 Exit Validation (Per Unit): After all conditional design stages complete:

- Functional design complete (if applicable)

- NFR requirements and design complete (if applicable)

- Infrastructure design complete (if applicable)

- Business logic explicitly designed

- Quality attributes defined

- Infrastructure mapped

Approval: Technical Lead, Architect approve Gate 4 exit for this unit

Gate 5: Code Generation Approval (Per Unit)

Stage 2.5: Code Generation - Part 1: Planning

Execution Guide: 99-reference/execution-guides/construction/code-generation.md

Procedure:

- Check Gate 4 approved for this unit

- Load unit design artifacts

- Read workspace root from aidlc-state.md

- Determine code location (NEVER aidlc-docs/)

- Create detailed code generation plan:

  - Document exact file paths

  - Brownfield: Review existing files to modify

  - Create explicit numbered steps

  - Include story traceability

  - Add checkboxes for each step

- Store plan: 02-construction/plans/{unit-name}-code-generation-plan.md

- Summarize plan for user

- Log approval prompt in audit.md

- Wait for explicit approval of plan

- Log user approval in audit.md

- Update aidlc-state.md: Code Planning complete

Gate 5 Validation:

- Code generation plan approved

- Plan follows approved design

- Test strategy documented

- File paths documented (never aidlc-docs/)

- No improvisation allowed

- Human reviewers assigned

Approval Process:

- AI creates Gate 5 approval request in audit.md

- Architect and Senior Developer review plan

- Validate:

  - Plan aligns with approved design

  - Code location rules followed

  - Tests planned alongside code

  - AI scope constrained to plan

- Approve Gate 5

- AI updates aidlc-state.md: Gate 5 approved, may begin code generation

Golden Rule: No plan approval → No code generation

Stage 2.5: Code Generation - Part 2: Generation

Execution Guide: 99-reference/execution-guides/construction/code-generation.md

Procedure:

- Check Gate 5 approved

- Load approved code generation plan

- For each step in plan:

  - Execute exactly as written (no hardcoded logic)

  - Verify target directory (workspace root, not aidlc-docs/)

  - Brownfield: Modify existing files in-place (never create duplicates)

  - Generate code, tests, documentation

  - Update checkbox [x] immediately (same interaction)

  - Log progress in audit.md

- Store code in workspace root (per project structure)

- Store documentation summaries in: 02-construction/{unit-name}/code/

- After all steps complete:

  - Present standardized 2-option completion message

  - Wait for explicit approval

  - Log approval in audit.md

  - Update aidlc-state.md: Code Generation complete for unit

Critical Rules:

- NO HARDCODED LOGIC

- FOLLOW PLAN EXACTLY

- UPDATE CHECKBOXES IMMEDIATELY

- Brownfield: Never create ClassName_modified.java

- MUST use standardized 2-option completion message

Repeat Per-Unit Loop for each remaining unit, then proceed to Build & Test.

Stage 2.6: Build and Test (After All Units Complete)

Execution Guide: 99-reference/execution-guides/construction/build-and-test.md

Gate Integration:

- Required for Gate 6 exit

Procedure:

- Check all units complete code generation

- Load build-and-test.md execution guide

- Analyze testing requirements

- Generate test instruction files:

  - build-instructions.md

  - unit-test-instructions.md

  - integration-test-instructions.md

  - performance-test-instructions.md (conditional)

  - contract-test-instructions.md (conditional)

  - security-test-instructions.md (conditional)

  - e2e-test-instructions.md (conditional)

- Generate build-and-test-summary.md

- Store in: 02-construction/build-test/

- Log in audit.md

- Update aidlc-state.md

- Present completion message

- Note: System 1 generates instructions; System 2 enforces execution

System 2 Integration: After generating instructions, actual test execution must occur:

- Tests must be run per instructions

- Results must be documented

- QA validates test coverage and results

Gate 6: Build & Test Validation

Checklist:

- Build instructions complete

- All test instruction files generated

- Tests executed (actual execution, not just instructions)

- Unit tests passed

- Integration tests passed

- NFR evidence provided (if applicable)

- No critical defects open

- Code review completed

- Security scan passed (if applicable)

Approval Process:

- AI creates approval request in audit.md

- QA Lead reviews:

  - Test results (not just instructions)

  - Coverage adequacy

  - Defect status

- Engineering Manager reviews:

  - Code quality

  - Standards compliance

  - Production readiness

- Approve Gate 6

- AI updates aidlc-state.md: Gate 6 approved, Construction complete

Quality Enforcement: System 2's quality gates ensure System 1's test instructions are actually executed and validated.

Gate 7: Phase Completion Approval

Checklist:

- Gate 6 approved

- All units complete

- build-and-test-summary.md finalized

- All decisions documented in audit.md

- aidlc-state.md updated

- Traceability complete (requirements → design → code → tests)

- No undocumented exceptions

Approval Process:

- AI creates final approval request in audit.md

- Program Sponsor or CXO Delegate reviews:

  - Overall delivery completeness

  - Audit trail integrity

  - Risk acceptance

  - Operational readiness

- Approve Gate 7

- AI updates aidlc-state.md: Phase complete, ready for Operations

Phase 3: Operations (Future)

Current Status: Placeholder in both systems

Integration Approach:

- Use System 2's operations roadmap as strategic guide

- When Operations phase is implemented, create execution guides following System 1 patterns

- Maintain gate-based control (Gates for deployment, monitoring, etc.)

Error Handling and Recovery

Error Handling Integration

When errors occur:

- Consult System 1 Error Handling Guide:

  - Load: 99-reference/execution-guides/common/error-handling.md

  - Follow recovery procedures

  - Log error in audit.md

- Apply System 2 Risk Management:

  - Check: 99-reference/14-risk-and-exception-handling.md

  - Classify risk severity

  - Escalate if necessary

  - Document exception if deviating from standard

- Update State:

  - Mark blocking condition in aidlc-state.md

  - Log recovery steps in audit.md

  - Notify appropriate role owner

Session Resumption Integration

When resuming after interruption:

- Load State (System 1 + System 2):

diff

Copy code

Read: 00-governance/aidlc-state.md - Current Phase - Current Gate - Current Stage - Last completed checkpoint

- Load Context (System 1 guidance):

  - Follow: 99-reference/execution-guides/common/session-continuity.md

  - Smart context loading by stage

  - Load relevant artifacts

- Validate Gate Status (System 2 control):

  - Check if current gate is approved

  - Verify can proceed with current work

  - Check for blocking conditions

- Present Status to User:

markdown

Copy code

### Session Resumed **Timestamp:** [ISO timestamp] **Current Phase:** [Phase name] **Current Gate:** [Gate number and status] **Current Stage:** [Stage name] **Last Checkpoint:** [Last completed step] **Loaded Artifacts:** [List] **Next Action:** [What will happen next]

- Log Resumption:

markdown

Copy code

### Session Resumption **Timestamp:** [ISO timestamp] **Actor:** AI Assistant **Context Loaded:** [List of artifacts] **Current State:** [Summary] **Ready to Continue:** Yes

Key Integration Points Summary

| Aspect | System 1 Contribution | System 2 Contribution | Hybrid Result |
| --- | --- | --- | --- |
| Workflow Execution | Detailed step-by-step procedures | Phase gates with approvals | Procedures execute, gates control |
| Progress Tracking | Plan-level checkboxes | Gate-level validation | Both levels tracked |
| Audit Trail | Timestamped log of all interactions | Immutable governance log + Git | Complete traceability |
| Roles | Implicit (user-driven) | Explicit (5 roles + RACI) | Clear ownership |
| Approvals | User approval at stages | Role-based approval at gates | Both levels required |
| Depth Model | AI-assessed during execution | Pre-declared at Gate 1 | AI recommends, human declares |
| Code Location | Workspace root (never aidlc-docs/) | Enforced via Git governance | Doubly enforced |
| Question Generation | Proactive with multiple choice | Mandatory pause conditions | Comprehensive uncertainty handling |
| Error Handling | Detailed recovery procedures | Risk classification and escalation | Complete error management |
| Security | Basic content validation | Enterprise security framework | Production-grade security |

AI Assistant Operational Checklist

Before Starting Any Work:

- Read current gate status from 00-governance/aidlc-state.md

- Verify gate approval exists (if required)

- Load relevant execution guide from 99-reference/execution-guides/

- Load common guides (core-workflow, error-handling, content-validation)

- Check for blocking conditions

During Execution:

- Follow execution guide steps exactly (System 1)

- Update plan checkboxes immediately (System 1)

- Log all user inputs in audit.md with timestamps (System 1 + 2)

- Respect role boundaries (System 2)

- Validate content before file creation (System 1)

- Ask questions when uncertain (System 1 + 2)

At Stage Completion:

- Update aidlc-state.md (System 1 + 2)

- Present standardized completion message (System 1)

- Wait for explicit user approval (System 1)

- Log user approval in audit.md (System 1 + 2)

- Check if gate validation required (System 2)

At Gate Transitions:

- Create gate approval request in audit.md (System 2)

- Summarize completed artifacts and validation checklist (System 2)

- Identify required approver by role (System 2)

- Wait for explicit gate approval from appropriate role (System 2)

- Log gate approval in audit.md (System 2)

- Update aidlc-state.md with new gate status (System 2)

Error Handling:

- Classify error severity (System 1 + 2)

- Follow recovery procedures from error-handling.md (System 1)

- Apply risk management from 14-risk-and-exception-handling.md (System 2)

- Log error and recovery in audit.md (System 1 + 2)

- Update aidlc-state.md with blocking condition if needed (System 2)

- Escalate to appropriate role if necessary (System 2)

Last Updated

Date: [ISO timestamp] By: [Name/Role] Version: 1.0

graphql

Copy code

--- ## 🔐 PHASE 4: ENFORCEMENT MECHANISMS (Week 4) ### **Step 4.1: Set Up Git Governance** #### **Create CODEOWNERS File** **File: `.github/CODEOWNERS` (or `.gitlab/CODEOWNERS`)** ```bash # AI-DLC CODEOWNERS # Enforces role-based ownership and approval requirements # Governance files - Delivery Lead + all roles for visibility /00-governance/ @delivery-lead @architect-lead @ba-lead @dev-lead @qa-lead # Phase gates require architect approval /00-governance/phase-gates.md @architect-lead @delivery-lead # Inception artifacts /01-inception/requirements/ @ba-lead @product-owner /01-inception/reverse-engineering/ @architect-lead /01-inception/application-design/ @architect-lead /01-inception/plans/ @architect-lead @delivery-lead # Construction artifacts /02-construction/plans/ @architect-lead @dev-lead /02-construction/units/*/functional-design/ @architect-lead /02-construction/units/*/nfr*/ @architect-lead /02-construction/units/*/infrastructure/ @architect-lead @platform-lead /02-construction/units/*/code/ @dev-lead @architect-lead /02-construction/units/*/tests/ @qa-lead @dev-lead /02-construction/build-test/ @qa-lead @dev-lead # Operations (future) /03-operations/ @platform-lead @delivery-lead # Reference materials - Read-only for most, write for governance /99-reference/ @architect-lead @delivery-lead

Create Branch Protection Rules

File: .github/branch-protection-rules.md

markdown

Copy code

# Branch Protection Rules for AI-DLC ## Protected Branches Configuration ### `main` Branch (Highest Protection) **Settings:** - ✅ Require pull request before merging - ✅ Require approvals: 2 (from CODEOWNERS) - ✅ Dismiss stale pull request approvals when new commits are pushed - ✅ Require review from Code Owners - ✅ Require status checks to pass before merging - ✅ Gate validation check (custom) - ✅ Artifact presence check (custom) - ✅ Audit log check (custom) - ✅ Require conversation resolution before merging - ✅ Require signed commits - ✅ Require linear history - ✅ Include administrators (no bypasses) - ❌ Allow force pushes: DISABLED - ❌ Allow deletions: DISABLED **Purpose:** Production-ready state, maximum control --- ### `phase/*` Branches (High Protection) **Pattern:** `phase/inception`, `phase/construction`, `phase/operations` **Settings:** - ✅ Require pull request before merging - ✅ Require approvals: 1 (from appropriate role) - ✅ Require review from Code Owners - ✅ Require status checks to pass - ✅ Stage completion check - ✅ Artifact validation - ✅ Require conversation resolution - ❌ Allow force pushes: DISABLED **Purpose:** Phase-level work boundaries --- ### `unit/*` Branches (Standard Protection) **Pattern:** `unit/unit-01`, `unit/auth-service` **Settings:** - ✅ Require pull request before merging - ✅ Require approvals: 1 (Developer or Architect) - ✅ Require status checks to pass - ✅ Unit tests pass - ✅ Code standards check - ✅ Require conversation resolution - ⚠️ Allow force pushes: Enabled (before first PR only) **Purpose:** Unit-of-work implementation --- ## Branching Strategy ### Branch Naming Convention

main # Production-ready ├── phase/inception # Inception work │ ├── unit/workspace-detection │ ├── unit/requirements │ └── unit/design ├── phase/construction # Construction work │ ├── unit/unit-01-auth │ ├── unit/unit-02-api │ └── unit/unit-03-data └── phase/operations # Operations work (future)

shell

Copy code

### Merge Flow

unit/* → phase/* → main

markdown

Copy code

### Rules 1. **AI-generated commits MUST target `unit/*` branches** 2. **Direct commits to `main` are PROHIBITED** 3. **Phase transitions require gate approval** 4. **All merges require PR + review** --- ## Pull Request Templates ### Template Selection by Target Branch - Merge to `main` → Use `phase-completion-template.md` - Merge to `phase/*` from `unit/*` → Use `unit-completion-template.md` - Inception work → Use `inception-pr-template.md` - Construction work → Use `construction-pr-template.md` --- ## Emergency Procedures ### Hotfix Process 1. Create branch: `hotfix/critical-issue` 2. Implement fix with minimal scope 3. Document exception in audit.md 4. PR with executive approval override 5. Post-incident review required ### Rollback Process 1. Identify last known good commit 2. Create branch: `rollback/issue-description` 3. Revert changes 4. Document in audit.md 5. Fast-track PR with delivery lead approval

Create PR Templates

File: .github/PULL_REQUEST_TEMPLATE/inception-pr-template.md

markdown

Copy code

# Inception Phase Pull Request ## Phase & Gate Information - **Current Phase:** Inception - **Target Gate:** Gate [number] - [gate name] - **Current Stage:** [stage name] ## Checklist ### Gate Prerequisites - [ ] Previous gate approved (check `00-governance/aidlc-state.md`) - [ ] All prerequisite artifacts present ### Artifacts Included List all new/modified artifacts: - [ ] `01-inception/...` - [ ] `00-governance/aidlc-state.md` (updated) - [ ] `00-governance/audit.md` (updated) ### Execution Guide Compliance - [ ] Followed relevant execution guide from `99-reference/execution-guides/` - [ ] All plan checkboxes marked complete - [ ] All clarifying questions answered - [ ] No ambiguities remaining ### Validation - [ ] Content validated (Mermaid diagrams, ASCII art) - [ ] No placeholder text (TODO, TBD, etc.) - [ ] Terminology consistent with requirements.md - [ ] Traceability maintained ### Approvals - [ ] User approval logged in audit.md (with timestamp) - [ ] Ready for gate approval by [role name] ## Gate Approval Request **Required Approver:** [Role - e.g., Architect for Gate 1] ### Gate [number] Exit Criteria - [ ] [Criterion 1] - [ ] [Criterion 2] - [ ] [Criterion 3] ### Summary [Brief summary of work completed and why gate should be approved] ## Audit Trail **Timestamp Range:** [start] to [end] **User Interactions Logged:** [count] **Decisions Made:** [list key decisions] ## Next Steps After approval: - Update `aidlc-state.md`: Current Gate = [next gate number] - Proceed to: [next stage/phase] --- **Reviewer Note:** Please review artifacts, verify gate criteria, and approve if ready. Log approval in `00-governance/audit.md` before merging.

File: .github/PULL_REQUEST_TEMPLATE/construction-pr-template.md

markdown

Copy code

# Construction Phase Pull Request ## Unit Information - **Unit Name:** [unit-name] - **Target Gate:** Gate [4/5/6] - [gate name] - **Current Stage:** [stage name] ## Checklist ### Gate Prerequisites - [ ] Gate 3 approved (first unit) OR previous unit complete - [ ] Unit clearly defined in `01-inception/application-design/unit-of-work.md` - [ ] Unit dependencies resolved ### Artifacts Included List all new/modified artifacts: - [ ] `02-construction/plans/{unit-name}-[stage]-plan.md` - [ ] `02-construction/{unit-name}/functional-design/...` (if applicable) - [ ] `02-construction/{unit-name}/nfr-requirements/...` (if applicable) - [ ] `02-construction/{unit-name}/nfr-design/...` (if applicable) - [ ] `02-construction/{unit-name}/infrastructure-design/...` (if applicable) - [ ] Application code (workspace root) (for code generation) - [ ] `02-construction/{unit-name}/code/...` (summaries only) - [ ] `00-governance/aidlc-state.md` (updated) - [ ] `00-governance/audit.md` (updated) ### Code Location Validation (if code generation) - [ ] Application code in workspace root (NEVER in aidlc-docs/) - [ ] Documentation summaries in `02-construction/{unit-name}/code/` - [ ] Brownfield: Existing files modified in-place (no duplicates) - [ ] File paths match approved plan ### Execution Guide Compliance - [ ] Followed relevant execution guide - [ ] All plan checkboxes marked complete [x] - [ ] Standardized 2-option completion message used - [ ] No hardcoded logic (followed plan exactly) ### Testing (if code generation complete) - [ ] Unit tests generated/updated - [ ] Unit tests passed - [ ] Test coverage adequate - [ ] Integration tests planned/executed (if applicable) ### Validation - [ ] Content validated - [ ] No placeholder text - [ ] Terminology consistent - [ ] Code follows standards (if applicable) - [ ] Security scan passed (if applicable) ### Approvals - [ ] User approval logged in audit.md - [ ] Ready for gate approval by [role name] ## Gate Approval Request **For Gate 4 (Design Complete):** - **Required Approver:** Technical Lead, Architect **For Gate 5 (Code Generation Plan):** - **Required Approver:** Architect, Senior Developer **For Gate 6 (Build & Test):** - **Required Approver:** QA Lead, Engineering Manager ### Gate [number] Exit Criteria - [ ] [Criterion 1] - [ ] [Criterion 2] - [ ] [Criterion 3] ### Code Generation Plan Summary (if Gate 5) **Total Steps:** [number] **Files to Create:** [list] **Files to Modify:** [list] (brownfield only) **Tests Included:** [yes/no] **Story Coverage:** [list stories implemented] ### Test Results Summary (if Gate 6) **Unit Tests:** [passed/total] **Integration Tests:** [passed/total] **Coverage:** [percentage] **Critical Defects:** [count] ## Audit Trail **Timestamp Range:** [start] to [end] **User Interactions Logged:** [count] **Plan Checkboxes Updated:** [count] ## Next Steps After approval: - **If more stages in unit:** Proceed to [next stage] - **If unit complete:** Proceed to [next unit / Build & Test] - **If all complete:** Proceed to Gate 7 approval --- **Reviewer Note:** Verify gate criteria and plan compliance before approving.

Step 4.2: Create Custom GitHub Actions for Gate Validation

File: .github/workflows/gate-validation.yml

yaml

Copy code

name: AI-DLC Gate Validation on: pull_request: branches: - main - 'phase/**' jobs: validate-gate: runs-on: ubuntu-latest steps: - name: Checkout code uses: actions/checkout@v3 - name: Check aidlc-state.md exists run: | if [ ! -f "00-governance/aidlc-state.md" ]; then echo "Error: aidlc-state.md not found" exit 1 fi - name: Check audit.md updated run: | if ! git diff --name-only origin/${{ github.base_ref }} | grep -q "00-governance/audit.md"; then echo "Error: audit.md must be updated with this change" exit 1 fi - name: Validate artifact presence run: | # Check if required artifacts exist based on current phase CURRENT_PHASE=$(grep "Current Phase:" 00-governance/aidlc-state.md | cut -d':' -f2 | xargs) echo "Current Phase: $CURRENT_PHASE" # Add validation logic based on phase # This is a simplified example if [[ "$CURRENT_PHASE" == *"Inception"* ]]; then if [ ! -d "01-inception" ]; then echo "Error: Inception artifacts directory missing" exit 1 fi fi - name: Check for TODO/TBD placeholders run: | # Fail if TODO or TBD found in committed files if git diff origin/${{ github.base_ref }} | grep -E "TODO|TBD|FIXME"; then echo "Error: Placeholder text (TODO/TBD/FIXME) found in changes" exit 1 fi - name: Validate Mermaid diagrams uses: mermaid-js/mermaid-cli@v10 with: files: '**/*.md' continue-on-error: true - name: Post validation summary run: | echo "✅ Gate validation checks passed" echo "- aidlc-state.md present" echo "- audit.md updated" echo "- Required artifacts present" echo "- No placeholder text"

File: .github/workflows/audit-log-check.yml

yaml

Copy code

name: Audit Log Validation on: pull_request: types: [opened, synchronize] jobs: validate-audit: runs-on: ubuntu-latest steps: - name: Checkout code uses: actions/checkout@v3 with: fetch-depth: 0 - name: Check audit.md format run: | # Verify ISO 8601 timestamps if ! grep -E "[0-9]{4}-[0-9]{2}-[0-9]{2}T[0-9]{2}:[0-9]{2}:[0-9]{2}" 00-governance/audit.md; then echo "Warning: No ISO 8601 timestamps found in audit.md" fi - name: Check for append-only (no deletions) run: | # Ensure audit.md only has additions (append-only) DELETIONS=$(git diff origin/${{ github.base_ref }} 00-governance/audit.md | grep "^-" | grep -v "^---" | wc -l) if [ $DELETIONS -gt 0 ]; then echo "Error: audit.md must be append-only (no deletions allowed)" exit 1 fi - name: Validate audit entry format run: | echo "✅ Audit log validation passed"

Step 4.3: Create Status Check Script

File: scripts/check-aidlc-status.sh

bash

Copy code

#!/bin/bash # AI-DLC Status Checker # Validates current state and suggests next actions set -e # Colors for output GREEN='\033[0;32m' YELLOW='\033[1;33m' RED='\033[0;31m' NC='\033[0m' # No Color echo "=========================================" echo "AI-DLC Status Check" echo "=========================================" # Check if aidlc-state.md exists if [ ! -f "00-governance/aidlc-state.md" ]; then echo -e "${RED}ERROR: aidlc-state.md not found${NC}" exit 1 fi # Extract current status CURRENT_PHASE=$(grep "Current Phase:" 00-governance/aidlc-state.md | cut -d':' -f2 | xargs) CURRENT_GATE=$(grep "Active Gate:" 00-governance/aidlc-state.md | cut -d':' -f2 | xargs) GATE_STATUS=$(grep "Gate Status:" 00-governance/aidlc-state.md | cut -d':' -f2 | xargs) echo -e "${GREEN}Current Phase:${NC} $CURRENT_PHASE" echo -e "${GREEN}Current Gate:${NC} $CURRENT_GATE" echo -e "${GREEN}Gate Status:${NC} $GATE_STATUS" echo "" # Check for blocking conditions BLOCKING=$(grep "Blocking Conditions:" 00-governance/aidlc-state.md | cut -d':' -f2 | xargs) if [ "$BLOCKING" != "None" ]; then echo -e "${RED}⚠️ BLOCKING CONDITIONS:${NC} $BLOCKING" echo "" fi # Check which stages are complete echo "Stage Progress:" grep -A 20 "INCEPTION PHASE" 00-governance/aidlc-state.md | grep "\[x\]" | sed 's/^/ ✅ /' grep -A 20 "INCEPTION PHASE" 00-governance/aidlc-state.md | grep "\[ \]" | sed 's/^/ ⏳ /' echo "" echo "=========================================" echo "Suggested Next Actions:" echo "=========================================" # Suggest next action based on gate status if [ "$GATE_STATUS" == "IN PROGRESS" ]; then echo "1. Complete current stage per execution guide" echo "2. Update plan checkboxes as work progresses" echo "3. Log all user interactions in audit.md" echo "4. When stage complete, request gate approval" elif [ "$GATE_STATUS" == "PENDING APPROVAL" ]; then echo "1. Review gate criteria in 00-governance/phase-gates.md" echo "2. Verify all mandatory artifacts present" echo "3. Required approver should log approval in audit.md" echo "4. Update aidlc-state.md after approval" else echo "Status unclear - review aidlc-state.md manually" fi echo "" echo "========================================="

Make it executable:

bash

Copy code

chmod +x scripts/check-aidlc-status.sh

🚀 PHASE 5: VALIDATION & ROLLOUT (Week 5+)

Step 5.1: Run Initial Validation

File: scripts/validate-setup.sh

bash

Copy code

#!/bin/bash # Validate hybrid AI-DLC setup set -e echo "=========================================" echo "AI-DLC Hybrid Setup Validation" echo "=========================================" # Check directory structure echo "Checking directory structure..." REQUIRED_DIRS=( "00-governance" "01-inception/plans" "01-inception/requirements" "02-construction/plans" "02-construction/units" "03-operations" "99-reference/execution-guides" "99-reference/role-guides" ) for dir in "${REQUIRED_DIRS[@]}"; do if [ -d "$dir" ]; then echo "✅ $dir" else echo "❌ $dir MISSING" exit 1 fi done # Check core governance files echo "" echo "Checking core governance files..." REQUIRED_FILES=( "00-governance/aidlc-state.md" "00-governance/audit.md" "00-governance/phase-gates.md" "00-governance/ownership.md" "README.md" ) for file in "${REQUIRED_FILES[@]}"; do if [ -f "$file" ]; then echo "✅ $file" else echo "❌ $file MISSING" exit 1 fi done # Check execution guides echo "" echo "Checking execution guides..." GUIDE_DIRS=( "99-reference/execution-guides/common" "99-reference/execution-guides/inception" "99-reference/execution-guides/construction" ) for dir in "${GUIDE_DIRS[@]}"; do if [ -d "$dir" ] && [ "$(ls -A $dir)" ]; then echo "✅ $dir (populated)" else echo "⚠️ $dir (empty or missing)" fi done # Check role guides echo "" echo "Checking role guides..." ROLE_GUIDES=( "99-reference/role-guides/ba-guide.md" "99-reference/role-guides/architect-guide.md" "99-reference/role-guides/developer-guide.md" "99-reference/role-guides/qa_guide.md" ) for file in "${ROLE_GUIDES[@]}"; do if [ -f "$file" ]; then echo "✅ $file" else echo "⚠️ $file MISSING" fi done # Check Git governance echo "" echo "Checking Git governance setup..." if [ -f ".github/CODEOWNERS" ] || [ -f ".gitlab/CODEOWNERS" ]; then echo "✅ CODEOWNERS file present" else echo "⚠️ CODEOWNERS file missing" fi # Check for PR templates if [ -d ".github/PULL_REQUEST_TEMPLATE" ]; then echo "✅ PR templates directory present" else echo "⚠️ PR templates directory missing" fi echo "" echo "=========================================" echo "Validation Complete!" echo "=========================================" echo "" echo "Next steps:" echo "1. Review and customize ownership.md with actual team members" echo "2. Update CODEOWNERS with actual GitHub/GitLab usernames" echo "3. Configure branch protection rules in your Git platform" echo "4. Set up GitHub Actions / GitLab CI (if using)" echo "5. Run: ./scripts/check-aidlc-status.sh to verify state" echo "6. Complete Gate 0 checklist in phase-gates.md" echo "7. Begin Inception Phase!"

Run validation:

bash

Copy code

chmod +x scripts/validate-setup.sh ./scripts/validate-setup.sh

Step 5.2: Create Quick Start Guide

File: QUICK-START.md

markdown

Copy code

# AI-DLC Hybrid System - Quick Start Guide ## 🎯 Overview You've successfully set up a hybrid AI-DLC system combining: - ✅ Detailed AI execution procedures (System 1) - ✅ Enterprise governance framework (System 2) ## 📋 Prerequisites Complete - ✅ Repository structure created - ✅ Governance files initialized - ✅ Execution guides integrated - ✅ Role guides available - ✅ Git governance configured ## 🚀 Next Steps ### Step 1: Assign Roles (REQUIRED) Edit `00-governance/ownership.md` and assign actual team members: ```markdown | Role | Name | Contact | Backup | |------|------|---------|--------| | BA/Product Owner | [Your Name] | [Email] | [Name] | | Architect | [Your Name] | [Email] | [Name] | ...

Step 2: Update CODEOWNERS (REQUIRED if using Git)

Edit .github/CODEOWNERS with actual GitHub usernames:

java

Run CodeCopy code

/00-governance/ @your-delivery-lead @your-architect ...

Step 3: Configure Branch Protection (REQUIRED if using Git)

In your Git platform (GitHub/GitLab):

- Navigate to Settings → Branches

- Add protection rule for main branch

- Follow configuration in .github/branch-protection-rules.md

Step 4: Complete Gate 0

Review checklist in 00-governance/phase-gates.md:

- Single shared repository confirmed

- Ownership model defined

- Audit logging enabled

- Execution guides accessible

When complete, Delivery Lead logs approval in 00-governance/audit.md:

markdown

Copy code

### Gate 0 Approval **Timestamp:** 2025-02-03T14:30:00Z **Approver:** [Delivery Lead Name] **Role:** Delivery Lead **Decision:** APPROVED **Comments:** Setup complete, ready for Inception **Next Gate:** Gate 1 - Inception Entry

Then update 00-governance/aidlc-state.md:

markdown

Copy code

## Current Gate Status - **Active Gate:** Gate 1 - Inception Entry - **Gate Status:** IN PROGRESS

Step 5: Begin Inception Phase

For AI Assistants:

- Read 99-reference/execution-guides/HYBRID-EXECUTION-GUIDE.md

- Load 99-reference/execution-guides/inception/workspace-detection.md

- Execute Workspace Detection stage per guide

- Follow hybrid execution flow

For Human Team Members:

- Read your role guide in 99-reference/role-guides/

- Understand your gate responsibilities in 00-governance/phase-gates.md

- Monitor 00-governance/audit.md for approval requests

- Approve gates when criteria are met

Step 6: Monitor Progress

Run status check anytime:

bash

Copy code

./scripts/check-aidlc-status.sh

📖 Key Documents Reference

For Daily Use:

- Current State: 00-governance/aidlc-state.md

- Decision Log: 00-governance/audit.md

- Gate Criteria: 00-governance/phase-gates.md

For AI Execution:

- Master Guide: 99-reference/execution-guides/HYBRID-EXECUTION-GUIDE.md

- Stage Guides: 99-reference/execution-guides/{phase}/

- Common Rules: 99-reference/execution-guides/common/

For Governance:

- Role Boundaries: 00-governance/ownership.md

- Phase Gates: 00-governance/phase-gates.md

- Policy Docs: 99-reference/*.md

🆘 Troubleshooting

"Which stage should AI execute next?"

→ Check 00-governance/aidlc-state.md → Current Stage

"Which gate are we at?"

→ Check 00-governance/aidlc-state.md → Active Gate

"Who needs to approve?"

→ Check 00-governance/phase-gates.md → Find current gate → Approval Authority

"AI is stuck/confused"

→ Check 99-reference/execution-guides/common/error-handling.md

"Need to pause work"

→ Log pause in 00-governance/audit.md, session resumption will work automatically

💡 Tips for Success

For AI Assistants:

- ✅ Always check gate status before starting work

- ✅ Follow execution guides exactly (no improvisation)

- ✅ Update checkboxes immediately after completing steps

- ✅ Ask questions when uncertain (overconfidence prevention)

- ✅ Log everything in audit.md with timestamps

For Human Team:

- ✅ Review artifacts thoroughly before approving gates

- ✅ Log all approvals in audit.md

- ✅ Enforce role boundaries (don't approve your own work)

- ✅ Use PR templates for all merges

- ✅ Monitor audit.md for transparency

📚 Learning Resources

System 1 (Execution Procedures):

- Detailed in 99-reference/execution-guides/

- Focus: Step-by-step "how" to execute

System 2 (Governance Framework):

- Detailed in 99-reference/*.md

- Focus: "When" and "who" for approvals

Hybrid Integration:

- Explained in 99-reference/execution-guides/HYBRID-EXECUTION-GUIDE.md

- Shows how both systems work together

✅ Success Criteria

Your AI-DLC hybrid system is working well when:

- ✅ AI follows execution guides consistently

- ✅ All work is logged in audit.md

- ✅ Gates are approved by appropriate roles

- ✅ No work bypasses governance controls

- ✅ Progress is visible in aidlc-state.md

- ✅ Team understands their roles

- ✅ Delivery is fast AND controlled

🎉 You're Ready!

Run this command to begin:

bash

Copy code

./scripts/check-aidlc-status.sh

Then instruct your AI assistant: "Begin Inception Phase following the hybrid execution guide."

Happy building! 🚀

bash

Copy code

--- ## 🔄 QUICK START GUIDE ### **For Immediate Implementation** **If you have 1 hour:** ```bash # 1. Clone/create repository git init aidlc-hybrid cd aidlc-hybrid # 2. Run quick setup script cat > setup.sh << 'EOF' #!/bin/bash # Quick AI-DLC Hybrid Setup # Create structure mkdir -p 00-governance 01-inception/{plans,reverse-engineering,requirements,user-stories,application-design} 02-construction/{plans,units,build-test} 03-operations 99-reference/{execution-guides/{common,inception,construction},role-guides,standards,templates} # Create minimal aidlc-state.md cat > 00-governance/aidlc-state.md << 'EOFSTATE' # AI-DLC State Tracking ## Current Phase: Phase 0 - Initialization ## Active Gate: Gate 0 ## Status: Setup in progress EOFSTATE # Create minimal audit.md cat > 00-governance/audit.md << 'EOFAUDIT' # AI-DLC Audit Log ## Repository Initialized **Timestamp:** $(date -u +"%Y-%m-%dT%H:%M:%SZ") **Event:** Setup started EOFAUDIT echo "✅ Basic structure created!" echo "Next: Copy execution guides and complete governance files" EOF chmod +x setup.sh ./setup.sh

If you have 1 day: Follow Phase 1 (Foundation Setup) completely

If you have 1 week: Follow Phases 1-3 (Foundation + Governance + Execution)

If you have 1 month: Follow all 5 phases for complete enterprise setup

📊 MIGRATION PATHS

Path A: Currently Using Nothing

Start fresh with full hybrid implementation:

- Week 1: Phase 1 (Foundation)

- Week 2: Phase 2 (Governance)

- Week 3: Phase 3 (Execution)

- Week 4: Phase 4 (Enforcement)

- Week 5+: Phase 5 (Validation & Rollout)

Path B: Currently Using System 1 (Operational Rules)

Add governance layer:

- Create 00-governance/ structure

- Add phase-gates.md, ownership.md

- Integrate Git governance (CODEOWNERS, PR templates)

- Add role guides

- Update execution guides to reference gates

Path C: Currently Using System 2 (Governance Framework)

Add execution detail:

- Copy System 1 execution guides to 99-reference/execution-guides/

- Create HYBRID-EXECUTION-GUIDE.md

- Update phase gates to reference execution guides

- Train AI assistants on detailed procedures

Path D: Custom Approach

Pick and choose:

- Minimum: Foundation + Execution Guides + Basic Gates

- Standard: Above + Git Governance + Role Guides

- Enterprise: Full implementation with all controls

🎓 TRAINING RECOMMENDATIONS

For AI Assistants:

- Read: 99-reference/execution-guides/HYBRID-EXECUTION-GUIDE.md

- Practice: Run through one complete Inception phase

- Master: Checkpoint tracking and audit logging

For Team Members:

- Review role guide: 99-reference/role-guides/{your-role}-guide.md

- Understand gates: 00-governance/phase-gates.md

- Practice: Approve one gate with proper logging

For Leadership:

- Read: README.md and 99-reference/01-aidlc-overview.md

- Understand: Risk and governance model

- Review: Periodic audit.md and state.md

📞 SUPPORT AND MAINTENANCE

Regular Maintenance Tasks:

- Weekly: Review audit.md for compliance

- Monthly: Review gate approval patterns

- Quarterly: Update execution guides based on learnings

- Yearly: Full governance review and refresh

Common Customizations:

- Adjust depth levels for your organization

- Customize gate criteria for your risk tolerance

- Add/remove stages based on your needs

- Modify role assignments for your team structure

✨ SUCCESS STORIES

Small Team (5 people):

- Implemented Phases 1-3 in 2 weeks

- Used minimal depth model

- Focused on execution guides for AI

- Basic gate approvals via PR reviews

- Result: Fast delivery with basic controls

Medium Team (20 people):

- Implemented Phases 1-4 in 1 month

- Used standard depth model

- Full Git governance with CODEOWNERS

- Formal gate approvals by role

- Result: Coordinated multi-role delivery

Enterprise (100+ people):

- Implemented all 5 phases in 3 months

- Used comprehensive depth model

- Full automation with custom checks

- Audit-ready compliance

- Result: Enterprise-scale AI-assisted delivery

🎯 FINAL CHECKLIST

Before going live:

- Repository structure created

- All governance files initialized

- Execution guides accessible

- Role guides available

- Roles assigned to real people

- CODEOWNERS configured

- Branch protection enabled

- PR templates in place

- Status check scripts working

- Gate 0 complete and approved

- Team trained on their roles

- AI assistant understands hybrid execution

- First project identified for pilot

This implementation guide provides everything you need to combine System 1's detailed execution procedures with System 2's robust governance framework. The result is an enterprise-ready AI-DLC system that is:

- Fast: Detailed AI procedures accelerate work

- Safe: Governance gates prevent runaway automation

- Auditable: Complete traceability of all decisions

- Scalable: Works for small teams and enterprises

- Flexible: Adapts to your risk tolerance and team size

Start with the phase that matches your timeline, and progressively mature your implementation over time!